## Sapirigamak District Format
Sapiri Gamak -People's Participatory Rural Development Programme- 2020
District:- |  | Colombo |  |  |  |  | District wise Monthly Physical and Financial Progress as at 15/ May/2020 | [24 empty] | Annexure 01
No. | DS Division | Projects * | [9 empty] | Allocation | [9 empty] | Physical Progress ** (No. of Projects) | [9 empty] | Expenditure (Rs. Mn) | No. of Beneficiaries
|  | No. of Projects Approved | Total categorized by Sectors * | [8 empty] | Approved Allocation (Rs.Mn) | Total Allocation Categorized by Sectors * | [8 empty] | A | B |  |  |  | C | D | E | F | G
|  |  | I | II | III | IV | V | VI | VII | VIII | IX |  | I | II | III | IV | V | VI | VII | VIII | IX |  | Estimates Approved & Bid Documents Prepared (B1) | Quotation / Bid called (B2) | Quotation / Bid Received (B3) | Contract Awarded (B4)
1 | Colombo
2 | Thibirigasyaya
3 | Kolonnawa
4 | Kotte
5 | Kaduwela
6 | Homagama
7 | Seethawaka
8 | Padukka | 155 | Total categorized by Sectors * I: 145; Total categorized by Sectors * IV: 6; Total categorized by Sectors * V: 1; Total categorized by Sectors * VI: 2; Total categorized by Sectors * IX: 1 | 92 | 84 |  |  | 3.5 | 0.5 | 2 |  |  | 2 | 9 | 116 | 23 | 7 | [7 empty] | 37681
9 | Kesbewa
10 | Maharagama
11 | Dehiwala
12 | Rathmalana
13 | Moratuwa
District Total |  | 155 | Total categorized by Sectors * I: 145; Total categorized by Sectors * IV: 6; Total categorized by Sectors * V: 1; Total categorized by Sectors * VI: 2; Total categorized by Sectors * IX: 1 | 92 | 84 |  |  | 3.5 | 0.5 | 2 |  |  | 2 | 9 | 116 | 23 | 7 | [7 empty] | 37681
* Projects should be categorized for following sectors
|  | Circular Code | Total categorized by Sectors * I: Sector name | [6 empty] | ** Physical progress
|  | I | Total categorized by Sectors * I: Village Roads, Culverts, Bridges, Side Drinage etc. | [6 empty] | A - Estimates are being / to be prepared
|  | II | Total categorized by Sectors * I: Warehouses Facilities for Agricultural Production | [6 empty] | B - For Constructions : B-1= Estimates Approved & Bid Documents Prepared, B-2= Quotation / Bid called, B-3= Quotation / Bid Received, B-4= Contract Awarded Other: Identified Institutions/ CBO's to provide Goods / Instruments, Obtain required list of goods, Estimated prepared
|  | III | Total categorized by Sectors * I: Economic Centers including Weekly Faires , Small Shops
|  | IV | Total categorized by Sectors * I: Construction and renovation of Small Tanks ,Canals, Anicuts,Ponds and Agricultural Wells
|  | V | Total categorized by Sectors * I: Community Drinking Water Supply Projects
|  | VI | Total categorized by Sectors * I: Development/Modernization of Rural Health Centers and Providing Facilities | [6 empty] | C - For Constructions : Start construction work,40% completed, Other : placed order for goods
|  | VII | Total categorized by Sectors * I: Providing and Developing Electricity, Water and Sanitary Facilities for Schools | [6 empty] | D - For Constructions : 60% completed Other : Received goods /instruments as per the order
|  | VIII | Total categorized by Sectors * I: Projects for Prevention of Disasters for Human habitants from wild Animals | [6 empty] | E - For Constructions 80% completed Other : Received goods /instruments as per the order
|  | IX | Total categorized by Sectors * I: Other Physical Infrastructure Improvement Projects Which are Directly Contibuted to Rural Economic Development | [6 empty] | G - For Constructions 100 Completed Other : Issued goods and instruments to identified institutions/CBOs

## Detail Report
499950.63
Sapiri Gamak -People's Participatory Rural Development Programme- 2020 | [35 empty] | 499757.49
District wise Monthly Physical and Financial Progress as at 15/May /2020 | [35 empty] | 499784.88
| Division : ……………………………… | Padukka | [33 empty] | 499987.49
1. Serial No | 2. Project No | 3 Name of the Project | 4 DS Division | GN Division |  | 7 Sector * | Key Performance Indicators |  | 10 Approved Amount (Rs.) | Total Estimated Cost (Rs.) |  | 13 Implementing Agency | 14 Name of the Contractor/ Society | Amount of Released Allocation |  |  | Progress | [14 empty] | 30 No of Beneficiaries | 31 Starting Date | 32 End Date | 33 Remarks | 499946.07
[17 empty] | Financial |  |  |  |  | Physical *** | [13 empty] | 499929.52
[10 empty] | 11 With Tax ( VAT) | 12 Without Tax (VAT) | [8 empty] | 21 Total Expenditure (Rs.) *2 | 22 % *3 | 23 A | 24 B |  |  |  | 25 C | 26 D | 27 E | 28 F | 29 G
|  |  |  | 5 GN Division No | 6 GN Division Name |  | 8 Length/Area (m./k.m./sq.m.) | 9 Value of Measurement | [5 empty] | 15 Without Admin (Rs) | 16 Admin (Rs) 0.5% | 17 Total (Rs) *1 | 18 Expenditure (Work Done) | 19 Tax (Vat,) | 20 Admin expenditure (0.5%) |  |  |  | B1 | B2 | B3 | B4 | [9 empty] | 499865.16
1 | 2020/SGP/PAD/452/001 | Construction the drain system from kotigalahena Church | Padukka | 452 | Galagedara east | I |  |  | 500000 |  | 499950.63 | Seethawaka Pradeshiya saba | [10 empty] | 1 | [8 empty] | 65 |  |  |  | 499862.27
2 | 2020/SGP/PAD/452/002 | Developing the first part of the satalight view road infront the mr: nanadana's home | Padukka |  |  | I |  |  | 500000 |  | 499757.49 | Seethawaka Pradeshiya saba | [10 empty] | 1 | [8 empty] | 65
3 | 2020/SGP/PAD/452/003 | Developing the road wich is going to pusweli mawatha wendesiwaththa | Padukka |  |  | I |  |  | 500000 |  | 499784.88 | Seethawaka Pradeshiya saba | [10 empty] | 1 | [8 empty] | 65 |  |  |  | 499553.88
4 | 2020/SGP/PAD/452/004 | developing the road from Mr: ralahami's house at Nidahas Mawatha | Padukka |  |  | I |  |  | 500000 |  | 499987.49 | Seethawaka Pradeshiya saba | [10 empty] | 1 | [8 empty] | 95 |  |  |  | 499735.36
5 | 2020/SGP/PAD/452/A/005 | developing the road from Mr:Dinasena pathiranage home to Mrs jayawathi's home at kammalpitiya waththa road | Padukka | 452/A | Galagedara North | I |  |  | 500000 |  | 499946.07 | Seethawaka Pradeshiya saba | [10 empty] | 1 | [8 empty] | 115 |  |  |  | 499733.1
6 | 2020/SGP/PAD/452/A/006 | Developing the road from bigining the pasal mawatha to plces by concreating | Padukka |  |  | I |  |  | 500000 |  | 499929.52 | Seethawaka Pradeshiya saba | [10 empty] | 1 | [8 empty] | 1750 |  |  |  | 499753.56
7 | 2020/SGP/PAD/452/A/007 | Rehabilitating the dammaged parts at samanala mawatha | Padukka |  |  | I |  |  | 500000 |  |  | Seethawaka Pradeshiya saba | [9 empty] | 1 | [9 empty] | 800 |  |  |  | 499937.12
8 | 2020/SGP/PAD/452/A/008 | Rehabilitating the remaining part by prinstan park road from Mr: sumith wasantha 's home ( circular road) | Padukka |  |  | I |  |  | 500000 |  | 499865.16 | Seethawaka Pradeshiya saba | [10 empty] | 1 | [8 empty] | 270 |  |  |  | 499937.12
9 | 2020/SGP/PAD/452/B/009 | developing the remaining part by cemetry road near the dialog tower | Padukka | 452/B | Galagedara south | I |  |  | 500000 |  | 499862.27 | Seethawaka Pradeshiya saba | [10 empty] | 1 | [8 empty] | 147
10 | 2020/SGP/PAD/452/B/010 | developing the moratuwa kanda road from bigining the paddy field to going to the padukka with culvert | Padukka |  |  | I |  |  | 1500000 |  |  | Seethawaka Pradeshiya saba | [9 empty] | 1 | [9 empty] | 1400 |  |  |  | 499860.22
11 | 2020/SGP/PAD/453/011 | developing the road near the main gate by pitumpe primary shool | Padukka | 453 | pitumpe North | I | m | 11.28*11.89 | 500000 |  | 499553.88 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 372 |  |  |  | 499937.12
12 | 2020/SGP/PAD/453/012 | Developing the galabadawaththa road Mr: rasika pradeep's home to ahead | Padukka |  |  | I | m | 111.89* 3.04878 | 500000 |  | 499735.36 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 143 |  |  | REQUESTING ALLOCATION | 499849.55
13 | 2020/SGP/PAD/453/013 | developing from bigining the by road of pabbatharama road | Padukka |  |  | I | m | 83.536* 2.439 | 500000 |  | 499733.1 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 40 |  |  | REQUESTING ALLOCATION | 499735.36
14 | 2020/SGP/PAD/453/014 | Developing the road with two side retainig wall near the comon well at annasigala hena | Padukka |  |  | I | m | 79.268* 2.439 | 500000 |  | 499753.56 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 54 |  |  | REQUESTING ALLOCATION | 499541.56
15 | 2020/SGP/PAD/453/A/015 | Developing road infront of the Mr: Adikari's home at galabadawaththa wendesi land | Padukka | 453/A | Wewalpanawa | I | m | 74.0853*3.0487 | 500000 |  | 499937.12 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 20 |  |  | REQUESTING ALLOCATION | 499998.28
16 | 2020/SGP/PAD/453/A/016 | Developing by road from bigining infront of the playground in wewalpanawa division | Padukka |  |  | I | m | 74.085* 3.048 | 500000 |  | 499937.12 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 20 |  |  | REQUESTING ALLOCATION | 499395.14
17 | 2020/SGP/PAD/453/A/017 | Developing the halgahakubura 1 anicut | Padukka |  |  | IV |  |  | 500000 |  |  | Provincial Irrigation office | [9 empty] | 1 | [9 empty] | 134 |  |  |  | 499541.56
18 | 2020/SGP/PAD/453/A/018 | Developing the walikeena road ( near the wendesi land) | Padukka |  |  | I | m | 53.353* 3.0487 | 500000 |  | 499860.22 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 81 |  |  | REQUESTING ALLOCATION | 499879.4
19 | 2020/SGP/PAD/453/B/019 | Developing the road from Mr Senevirathna 'shome at Somananda Mawatha Kotigalahena road | Padukka | 453/B | Pitumpe South | I | m | 74.085* 3.0487 | 500000 |  | 499937.12 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 1410 |  |  | REQUESTING ALLOCATION | 499917.23
20 | 2020/SGP/PAD/453/B/020 | Developing the cross road at right side with shoe culvert at left side by road near the transformer at somananda mawatha | Padukka | 453/B | Pitumpe South | I | m | 24.39* 4.57 31.4* 3.658 | 500000 |  | 499849.55 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 1370 |  |  | REQUESTING ALLOCATION | 499617.43
21 | 2020/SGP/PAD/453/B/021 | Developing the road from Mr Chithrasena's home to ahead at left side cross road of by road of Somananda mawatha (near transformer) | Padukka | 453/B | Pitumpe South | I | m | 111.89* 3.0487 | 500000 |  | 499735.36 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 100 |  |  | REQUESTING ALLOCATION | 499998.29
22 | 2020/SGP/PAD/454/022 | Developing the by road near the Ganelanda temple at Ganelanda | Padukka | 454 | Uggalla | I |  | 132* 2.439 | 500000 |  | 499541.56 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 175 |  |  | REQUESTING ALLOCATION | 499948.87
23 | 2020/SGP/PAD/454/023 | Developing the Delgahawaththa by road near Mr Wajira's home at Sirisumana Mawatha | Padukka | 454 | Uggalla | I | m | 92.073* 2.439 | 500000 |  | 499998.28 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 165 |  |  | REQUESTING ALLOCATION | 499937.12
24 | 2020/SGP/PAD/454/024 | Developing the by road from Fawsi Mawatha pelennagahawaththa Wendesiwaththa | Padukka | 454 | Uggalla | I | m | 119.512* 2.743 | 500000 |  | 499395.14 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 237 |  |  | REQUESTING ALLOCATION | 499862.19
25 | 2020/SGP/PAD/454/025 | Developing the Beligahawaththa road from Mr Sameera's home to ahead | Padukka | 454 | Uggalla | I | m | 132.01* 2.439 | 500000 |  | 499541.56 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 293 |  |  | REQUESTING ALLOCATION
26 | 2020/SGP/PAD/454/A/026 | Developing the road from Mr Nimal's home to Mr Daniyal's home at Angampitiya Gola road (by road of Gola road) | Padukka | 454/A | Angampitiya | I | m | 92.07* 2.439 | 500000 |  | 499879.4 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 37 |  |  | REQUESTING ALLOCATION | 499735.12
27 | 2020/SGP/PAD/454/A/027 | Developing the road near the Angampitiya Nilasewana from finished place by road to ahead | Padukka | 454/A | Angampitiya | I | m | 83.536* 2.439 | 500000 |  | 499917.23 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 37 |  |  | REQUESTING ALLOCATION | 499246.64
28 | 2020/SGP/PAD/454/A/028 | Developing the road from main road to Mr. Anil's home near the temple | Padukka | 454/A | Angampitiya | I | m | 91.463* 2.439 | 500000 |  | 499617.43 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 30 |  |  | REQUESTING ALLOCATION | 499493.29
29 | 2020/SGP/PAD/454/A/029 | Developing the Milladeniya second by road from finished place by road to ahead | Padukka | 454/A | Angampitiya | I | m | 92.07* 2.439 | 500000 |  | 499998.29 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 62 |  |  | REQUESTING ALLOCATION | 499493.29
30 | 2020/SGP/PAD/454/B/030 | Developing the Morabawila road from Mr H .Pemadasa's home to ahead | Padukka | 454/B | Halpe | I | m | 119.5* 2.74 | 500000 |  | 499948.87 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 69 |  |  | REQUESTING ALLOCATION | 999676.8
31 | 2020/SGP/PAD/454/B/031 | Developing the road from beginning of Minwisithurugama second by road | Padukka | 454/B | Halpe | I | m | 74.085* 3.0487 | 500000 |  | 499937.12 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 101 |  |  | REQUESTING ALLOCATION | 499998.28
32 | 2020/SGP/PAD/454/B/032 | Developing the first by road of Pussagala road from Mr Nihal's home to ahead | Padukka | 454/B | Halpe | I | m | 132.01* 2.43 | 500000 |  | 499862.19 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 175 |  |  |  | 499937.12
33 | 2020/SGP/PAD/454/B/033 | Developing the Halpe Milladeniya road near Mr Shantha's home to ahead | Padukka | 454/B | Halpe | I |  |  | 500000 |  |  | D.S Office Padukka | [9 empty] | 1 | [9 empty] | 111 |  |  |  | 499998.28
34 | 2020/SGP/PAD/455/034 | Developing the Puwakgahawela road from the community hall to ahead | Padukka | 455 | Weragala | I | m | 74.085* 3.048 | 500000 |  | 499735.12 | D.S Office Padukka |  | 494787.26 | 2473.93 | 497261.19 | [7 empty] | 1 | [7 empty] | 250 |  |  |  | 499129.12
35 | 2020/SGP/PAD/455/035 | Developing the second lane of Dale state from begging to ahead | Padukka | 455 | Weragala | I | m | 74.085* 3.048 | 500000 |  | 499246.64 | D.S Office Padukka |  | 494303.6 | 2471.52 | 496775.12 | [7 empty] | 1 | [7 empty] | 110 |  |  |  | 499998.28
36 | 2020/SGP/PAD/455/036 | Developing the Janasavi Mawatha at weragala from Mr Ananda's bautique to ahead | Padukka | 455 | Weragala | I | m | 92.073* 2.439 | 500000 |  | 499493.29 | D.S Office Padukka |  | 494547.81 | 2472.74 | 497020.55 | [7 empty] | 1 | [7 empty] | 80 |  |  |  | 499998.28
37 | 2020/SGP/PAD/455/037 | Developing the remaing parts ( with out developing parts) of Weragala Horalanda Mawatha | Padukka | 455 | Weragala | I | m | 92.073* 2.439 | 500000 |  | 499493.29 | D.S Office Padukka |  | 494547.81 | 2472.74 | 497020.55 | [7 empty] | 1 | [7 empty] | 45 |  |  |  | 499998.29
38 | 2020/SGP/PAD/455/A/038 | Developing the Gangoda road with culvert at the Mahinhala | Padukka | 455/A | Mahinhala | I | m | 91.46* 2.439 | 1000000 |  | 999676.8 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 87 |  |  | REQUESTING ALLOCATION | 499943.59
39 | 2020/SGP/PAD/455/A/039 | Developing the road which go to housing scheme at Mahingala Padukka watta | Padukka | 455/A | Mahingala | I | m | 92.073* 2.439 | 500000 |  | 499998.28 | D.S Office Padukka |  | 495047.8 | 2475.24 | 497523.04 | [8 empty] | 1 | [6 empty] | 131 |  |  |  | 499995.46
40 | 2020/SGP/PAD/455/A/040 | Developing the Delgahapitiya road at Mahingala | Padukka | 455/A | Mahinhala | I | m | 74.085* 3.0487 | 500000 |  | 499937.12 | D.S Office Padukka |  | 494987.24 | 2474.94 | 497462.18 | [8 empty] | 1 | [6 empty] | 110 |  |  |  | 499890.9
41 | 2020/SGP/PAD/456/044 | Developing the Kandawatta main road from Mr. Chithrananda home's to ahead | Padukka | 456 | Pinnawala North | I | m | 92.073* 2.439 | 500000 |  | 499998.28 | D.S Office Padukka |  | 495047.8 | 2475.24 | 497523.04 | [7 empty] | 1 | [7 empty] | 25 |  |  |  | 499990.03
42 | 2020/SGP/PAD/456/A/045 | Developing the road which go to Morakale railway Station (near the Bungalo) | Padukka | 456/A | Pinnawala South | I | m | 74.085* 3.0487 | 500000 |  | 499129.12 | D.S Office Padukka |  | 494187.24 | 2470.94 | 496658.18 | [7 empty] | 1 | [7 empty] | 600 |  |  |  | 999984.89
43 | 2020/SGP/PAD/456/A/046 | Developing the Alubogahalanda road(near the Mr. Thilaka's home) | Padukka | 456/A | Pinnawala South | I | m | 92.073* 2.439 | 500000 |  | 499998.28 | D.S Office Padukka |  | 495047.8 | 2475.24 | 497523.04 | [7 empty] | 1 | [7 empty] | 60 |  |  |  | 499865.89
44 | 2020/SGP/PAD/456/A/047 | Developing the road from Baludiyalanda II road(from Waga Padukka road to Ms. K.P.D. Karunawathi 's home ) | Padukka | 456/A | Pinnawala South | I | m | 92.073* 2.439 | 500000 |  | 499998.28 | D.S Office Padukka |  | 495047.8 | 2475.24 | 497523.04 | [7 empty] | 1 | [7 empty] | 80 |  |  |  | 499975.79
45 | 2020/SGP/PAD/456/A/048 | Developing the Alubogahalanda road(near the Mr. Thilaka's home) | Padukka | 456/A | Pinnawala South | I | m | 92.07* 2.439 | 500000 |  | 499998.29 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 30 |  |  |  | 499943.59
46 | 2020/SGP/PAD/457/049 | Developing the road from Janasavi Mawatha near the Mr.Leel's home | Padukka | 457 | Waga Easte | I | m | 83.536* 2.439 | 500000 |  | 499943.59 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 103 |  |  | REQUESTING ALLOCATION | 499975.79
47 | 2020/SGP/PAD/457/050 | Developing the road which go to the Henyaya Community hall | Padukka | 457 | Waga Easte | I | m | 132*2.74 | 500000 |  | 499995.46 | D.S Office Padukka |  | 495045.02 | 2475.22 | 497520.24 | [8 empty] | 1 | [6 empty] | 155 |  |  |  | 499790.5
48 | 2020/SGP/PAD/457/051 | Developing the Halpe watta new House road (from begining) | Padukka | 457 | Waga Easte | I | m | 81.097* 2.743 | 500000 |  | 499890.9 | D.S Office Padukka |  | 494941.5 | 2474.7 | 497416.2 | [8 empty] | 1 | [6 empty] | 170
49 | 2020/SGP/PAD/457/052 | Developing the by road from Mr.Ajith's home at Janaudanagam waga Iridapola | Padukka | 457 | Waga Easte | I | m | 56.402* 2.439 | 500000 |  | 499990.03 | D.S Office Padukka |  | 495039.63 | 2475.2 | 497514.83 | [8 empty] | 1 | [6 empty] | 40 |  |  |  | 499996.51
50 | 2020/SGP/PAD/457/A/053 | Developing the Mahayaya road from Mr.W.Chandrasiri's home to ahead | Padukka | 457/A | Waga West | I | m | 150.91* 3.048 | 1000000 |  | 999984.89 | D.S Office Padukka |  | 990084.05 | 4950.42 | 995034.47 | [7 empty] | 1 | [7 empty] | 400 |  |  |  | 499756.74
51 | 2020/SGP/PAD/457/A/054 | Developing the Mawaragodalla road from Mrs. Suvinitha's home to ahead | Padukka | 457/A | Waga West | I | m | 73.17* 3.0487 | 500000 |  | 499865.89 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 330 |  |  | REQUESTING ALLOCATION | 999949.89
52 | 2020/SGP/PAD/457/A/055 | Developing the road near Mr. Karunachandra's home to mrs.Wimala Wijewardana's home. | Padukka | 457/A | Waga West | I | m | 90.853* 2.439 | 500000 |  | 499975.79 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 440 |  |  |  | 499733.1
53 | 2020/SGP/PAD/457/B/057 | Development of the road wilaudakanda near Mr;Munidasa's Home to the Pallewasala main road. | Padukka | 457/B | Waga North | I |  |  | 500000 |  | 499943.59 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 43 |  |  |  | 499997.71
54 | 2020/SGP/PAD/457/B/058 | Developing the Eluwagala temple road from beginning. | Padukka | 457/B | Waga North | I | m | 90.85* 2.439 | 500000 |  | 499975.79 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 27 |  |  |  | 499862.9
55 | 2020/SGP/PAD/457/C/059 | Development of the small bridge near at Mrs.Geethani Kariyawasam's home | Padukka | 457/C | Waga south | I | m | 52.134* 2.743 | 500000 |  | 499790.5 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 265
56 | 2020/SGP/PAD/457/C/060 | Developing the samagi Prajajala Water project.of waga south | Padukka | 457/C | Waga south | V |  |  | 500000 |  | 499963.43 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 375 |  |  |  | 499733.1
57 | 2020/SGP/PAD/457/C/061 | Construction of the side Wall of to Mr.Amitha's home | Padukka | 457/C | Waga south | IV | m | 17.68 | 500000 |  | 499996.51 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 20 |  |  |  | 999975.95
58 | 2020/SGP/PAD/457/C/062 | Development of the Iddagasdeniya road forward From Mr.upul's home | Padukka | 457/C | Waga south | I | m | 136*2.74 | 500000 |  | 499756.74 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 170 |  |  | REQUESTING ALLOCATION | 499733.1
59 | 2020/SGP/PAD/458/063 | Development of the project Udagama old road From Mr.Dinik methsiri Dissanayaka 's home to Mr.W.Manjula saman kumara's home | Padukka | 458 | Udagama | I | m | 170.731*2.439 | 1000000 |  | 999949.89 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 101 |  |  | REQUESTING ALLOCATION | 499639.53
60 | 2020/SGP/PAD/458/064 | Development of the main by road at "Loka darshana mawatha"From Mr.J. Gunasena's land. | Padukka | 458 | Udagama | I | m | 83.536* 2.439 | 500000 |  | 499733.1 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 31 |  |  | REQUESTING ALLOCATION | 499996.51
61 | 2020/SGP/PAD/458/A/065 | Development of the Labugama Waththa road With Culvert Infront of the Kovila from the Concreeted place. | Padukka | 458/A | Tummodara | I | m | 3.658* 4.878 | 500000 |  | 499997.71 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 67 |  |  | REQUESTING ALLOCATION | 499963.44
62 | 2020/SGP/PAD/458/A/066 | Development of the Ambagasyaya -Wendesi Waththa by road From tha Concreetad place | Padukka | 458/A | Tummodara | I | m | 73.475* 3.048 | 500000 |  | 499862.9 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 66 |  |  |  | 499683.97
63 | 2020/SGP/PAD/458/A/067 | Developing the Polwaththa Second by road from main road ( with must be develop the by road) | Padukka | 458/A | Tummodara | I | m | 322* 2.439 | 500000 |  | 482469.83 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 217 |  |  |  | 499986.26
64 | 2020/SGP/PAD/458/A/068 | Development of the Tummodara by road From the Finished place to ahead. | Padukka | 458/A | Tummodara | I | m | 83.536* 2.439 | 500000 |  | 499733.1 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 38 |  |  | REQUESTING ALLOCATION | 499937.12
65 | 2020/SGP/PAD/458/B/069 | Development of the side Wall With Culvert of Ihala Vela Gurulana From Mr. w.v. Laksman's paddy field. | Padukka | 458/B | Gurulana | I | m | 30.48 | 1000000 |  | 999975.95 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 52 |  |  | REQUESTING ALLOCATION | 499511.24
66 | 2020/SGP/PAD/458/B/070 | Development of the road to tha Cemetry near Mr.Pramasiri Abesingha From Mrs. N.Leelawathe's land. | Padukka | 458/B | Gurulana | I | m | 83.536* 2.439 | 500000 |  | 499733.1 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 375 |  |  | REQUESTING ALLOCATION | 499937.12
67 | 2020/SGP/PAD/458/B/071 | Development of the Mian by road with culverts from the beginning at Janasavi Mawatha. | Padukka | 458/B | Gurulana | I | m | 59.75* 2.743 | 500000 |  | 499639.53 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 37 |  |  |  | 798793.35
68 | 2020/SGP/PAD/458/C/072 | Constructing the retaining wall at bend area of Dangahakubura road (ahead the retaining wall) | Padukka | 458/C | Dabora | I | m | 17.682 | 500000 |  | 499996.51 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 409 |  |  |  | 499617.59
69 | 2020/SGP/PAD/458/C/073 | Developing by the common road which go to the Praja well near transformer | Padukka | 458/C | Dabora | I | m | 36.585* 2.439 | 500000 |  | 499963.44 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 399 |  |  |  | 499930
70 | 2020/SGP/PAD/458/C/074 | Developing the down road from Mr.Chandrasoma's home at Dabora Heenyaya | Padukka | 458/C | Dabora | I | m | 17.68 | 500000 |  | 499683.97 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 39 |  |  | REQUESTING ALLOCATION | 499617.6
71 | 2020/SGP/PAD/458/C/075 | From Developing down road near by the Henyaya Mr.Nimal's residence | Padukka | 458/C | Dabora | I | m | 74.69* 2.743 | 500000 |  | 499986.26 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 30 |  |  | REQUESTING ALLOCATION | 499934.14
72 | 2020/SGP/PAD/459/076 | Developing the main road with by road end of the Isuru Uyana road near Mr.Chandana's home | Padukka | 459 | Ihala bope | I | m | 74.08* 3.04 | 500000 |  | 499937.12 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 119 |  |  | REQUESTING ALLOCATION | 499634.58
73 | 2020/SGP/PAD/459/077 | Developnig the Degamthilaka mawatha from bigining | Padukka | 459 | Ihala bope | I | m | 61.89* 3.65 | 500000 |  | 499511.24 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 122 |  |  | REQUESTING ALLOCATION
74 | 2020/SGP/PAD/459/078 | From Developing road near by Mr.G.Gamini Premathilaka residence | Padukka | 459 | Ihala bope | I | m | 74.08* 3.04 | 500000 |  | 499937.12 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 79 |  |  | REQUESTING ALLOCATION | 499978.53
75 | 2020/SGP/PAD/459/079 | FromDeveloping road near by the end of the Rajasingha Primary School | Padukka | 459 | Ihala bope | I | m | 43.29* 2.74 | 500000 |  | 498793.35 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 576 |  |  |  | 499937.12
76 | 2020/SGP/PAD/459/A/080 | Developing the 1st lane near by Kurundeniyaroad (Front of the Mis.R.A.LeemaShanthi's residence) | Padukka | 459/A | Pahala bope | I | m | 74.085* 3.0487 | 500000 |  | 499617.59 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 43 |  |  | REQUESTING ALLOCATION | 499472.24
77 | 2020/SGP/PAD/459/A/081 | Developning 2nd Lane near by Kurundeniya road (near by Mr.Kulatunga's residence) | Padukka | 459/A | Pahala bope | I | m | 82.317* 2.7439 | 500000 |  | 499930 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 27 |  |  | REQUESTING ALLOCATION | 499937.12
78 | 2020/SGP/PAD/459/A/082 | From Developing Baduwaththa road | Padukka | 459/A | Pahala bope | I | m | 74.085* 3.0487 | 500000 |  | 499617.6 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 19 |  |  | REQUESTING ALLOCATION | 499710.53
79 | 2020/SGP/PAD/459/A/083 | Developing the Aswedduma road from Mr.Wijelal's residence | Padukka | 459/A | Pahala bope | I | m | 20.73 | 500000 |  | 499934.14 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 71 |  |  |  | 999932.8
80 | 2020/SGP/PAD/459/B/084 | Constructing Tractor Crossing near by Galpoththa Welyaya | Padukka | 459/B | Siyabalawa | I | Tractor crossing |  | 500000 |  | 499634.58 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 75 |  |  |  | 499274.66
81 | 2020/SGP/PAD/459/B/085 | Costructing a bridge across Belidola to end of the Rathugama | Padukka | 459/B | Siyabalawa | I |  |  | 1000000 |  |  | PRDA | [9 empty] | 1 | [9 empty] | 2420 |  |  |  | 499937.1
82 | 2020/SGP/PAD/459/B/086 | Constructing Siyabalawa side drain (Front of Sumith Wasantha's residence) | Padukka | 459/B | Siyabalawa | I | m | 30.48 | 500000 |  | 499978.53 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 2370 |  |  | REQUESTING ALLOCATION | 499620.69
83 | 2020/SGP/PAD /460/087 | Developing the road from Uppalawannaramya to Mohomad Kade at Arukwaththa | Padukka | 460 | Arukkwaththa North | I | m | 74.08* 3.04 | 500000 |  | 499937.12 | D.S Office Padukka |  | 494987.24 | 2474.94 | 497462.18 | [7 empty] | 1 | [7 empty] | 350 |  |  |  | 499998.28
84 | 2020/SGP/PAD/460/088 | Developing right turned road infront of the Uppalawannaramaya near by No:352/3/1 Mr.R.P.Pathmasiri's residence | Padukka | 460 | Arukkwaththa North | I | m | 60.97* 3.04 | 500000 |  | 499472.24 | D.S Office Padukka |  | 494526.98 | 2472.63 | 496999.61 | [7 empty] | 1 | [7 empty] | 42 |  |  |  | 499998.28
85 | 2020/SGP/PAD/460/089 | Developing the road (hill side)near Mr.Amarasingha's residence at green terase at Arukwaththa. | Padukka | 460 | Arukkwaththa North | I | m | 74.08* 3.04 | 500000 |  | 499937.12 | D.S Office Padukka |  | 494987.24 | 2474.94 | 497462.18 | [7 empty] | 1 | [7 empty] | 200 |  |  |  | 499998.28
86 | 2020/SGP/PAD/460/090 | From developing road near by boarder of North Weliowita Kubura to Mrs.Kanchana's recidence | Padukka | 460 | Arukkwaththa North | I | m | 82.31* 2.74 | 500000 |  | 499710.53 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 80 |  |  | REQUESTING ALLOCATION | 499650.64
87 | 2020/SGP/PAD/460/A/091 | Development of Main Entrance Section of Mahamaya Place Road (from opposite theHalgaha Yata Kade) | Padukka | 460/A | Arukkwatha south | I | m | 128.65* 3.04 | 1000000 |  | 999932.8 | D.S Office Padukka |  | 990032.48 | 4950.16 | 994982.64 | [7 empty] | 1 | [7 empty] | 250 |  |  |  | 499676.44
88 | 2020/SGP/PAD/460/A/092 | Concreting culvert system at Gajamawatta road (from Lalith Udaya Kumara's land to the end) | Padukka | 460/A | Arukkwatha south | I | m | 26.219 | 500000 |  | 499274.66 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 260 |  |  |  | 499903.09
89 | 2020/SGP/PAD/460/A/093 | Development of Jayasundara Place main road (near the Lalith kumara's home) | Padukka | 460/A | Arukkwatha south | I | m | 74.08* 3.04 | 500000 |  | 499937.1 | D.S Office Padukka |  | 494987.22 | 2474.94 | 497462.16 | [7 empty] | 1 | [7 empty] | 300 |  |  |  | 499903.09
90 | 2020/SGP/PAD/460/B/094 | Developing the retaining wall along the Dola road near the Ganegoda Amarasinghe Mawatha community center | Padukka | 460/B | Ganegoda | IV | m | 28.96 | 500000 |  | 499620.69 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 460 |  |  |  | 499493.29
91 | 2020/SGP/PAD/460/B/095 | Development of right of way near the house of Mr. Ranjith Kumarasinghe, No. 157/A, 2nd lane near Ganegoda Bodhiya | Padukka | 460/B | Ganegoda | I | m | 92.07* 2.43 | 500000 |  | 499998.28 | D.S Office Padukka |  | 495047.8 | 2475.24 | 497523.04 | [7 empty] | 1 | [7 empty] | 60 |  |  |  | 499866.83
92 | 2020/SGP/PAD/460/B/096 | Development of road leading to K.G. Sunil's house at Arukwatta Ganegoda Thambilwatta road | Padukka | 460/B | Ganegoda | I | m | 92.07* 2.43 | 500000 |  | 499998.28 | D.S Office Padukka |  | 495047.8 | 2475.24 | 497523.04 | [7 empty] | 1 | [7 empty] | 95 |  |  |  | 499493.29
93 | 2020/SGP/PAD/460/B/097 | Developing the Krushi road to the left from the Buddha shrine which connects Ganegoda and Arukwatta North | Padukka | 460/B | Ganegoda | I | m | 92.07* 2.43 | 500000 |  | 499998.28 | D.S Office Padukka |  | 495047.8 | 2475.24 | 497523.04 | [7 empty] | 1 | [7 empty] | 100 |  |  |  | 499803
94 | 2020/SGP/PAD/461/098 | Development of Jayanthipura Mawatha, Jayanthipura Second Narrow Road (near the residence of Mr. Ariyapala) | Padukka | 461 | Padukka | I | m | 74.085* 3.048 | 500000 |  | 499650.64 | D.S Office Padukka |  | 494703.6 | 2473.52 | 497177.12 | [7 empty] | 1 | [7 empty] | 55 |  |  |  | 499998.98
95 | 2020/SGP/PAD/461/099 | Developing the side wall of the road from the end of the Dampitiya road. | Padukka | 461 | Padukka | I | m | 27.13 | 500000 |  | 499676.44 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 163 |  |  |  | 499951.15
96 | 2020/SGP/PAD/461/100 | Development of Senanayake Place 4th Avenue from the beginning. | Padukka | 461 | Padukka | I | m | 67.073* 3.353 | 500000 |  | 499903.09 | D.S Office Padukka |  | 494953.55 | 2474.77 | 497428.32 | [7 empty] | 1 | [7 empty] | 17 |  |  |  | 499683.66
97 | 2020/SGP/PAD/461/101 | Developing the road Pussali Oya Pallekadewatta near the Mr. Bandu's home. | Padukka | 461 | Padukka | I | m | 67.073* 3.353 | 500000 |  | 499903.09 | D.S Office Padukka |  | 494953.55 | 2474.77 | 497428.32 | [7 empty] | 1 | [7 empty] | 17 |  |  |  | 499962.68
98 | 2020/SGP/PAD/461/A/102 | Developing the damaged part of Alupotha road starting point. | Padukka | 461/A | Angamuwa | I | m | 92.073* 2.439 | 500000 |  | 499493.29 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 190 |  |  | REQUESTING ALLOCATION | 499860.23
99 | 2020/SGP/PAD/461/A/103 | 324/2 side of the Sihilalpura interchange, development of the road from Mr. Ajith's home | Padukka | 461/A | Angamuwa | I | m | 77.13* 4.57 | 500000 |  | 499866.83 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 140 |  |  | REQUESTING ALLOCATION | 499655.61
100 | 2020/SGP/PAD/461/A/104 | Development of road leading to Mr. Dhammika's home, 74 th part of Ganigelanda road. | Padukka | 461/A | Angamuwa | I | m | 92.073* 2.439 | 500000 |  | 499493.29 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 75 |  |  | REQUESTING ALLOCATION | 498855.89
101 | 2020/SGP/PAD/461/A/105 | End of Kanukattiya road (towards auction land) 169 / B road development near the residence of Mr. Ajith Prasanna | Padukka | 461/A | Angamuwa | I | m | 45.73* 2.439 37.195* 3.0487 | 500000 |  | 499803 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 60 |  |  | REQUESTING ALLOCATION | 499779.41
102 | 2020/SGP/PAD/461/B/106 | Development of road leading to the houses of Mr. K.D.S. Kumara, Kottawatta, Udumulla. | Padukka | 461/B | Udumulla | I | m | 53.963* 3.0487 | 500000 |  | 499998.98 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 230 |  |  | REQUESTING ALLOCATION | 499995.46
103 | 2020/SGP/PAD/461/B/107 | Developing the road leading to Mr. Dammika's residence on the left side of the main road at Udumulla Kottawatta road. | Padukka | 461/B | Udumulla | I | m | 90.853* 2.439 | 500000 |  | 499951.15 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 62 |  |  | REQUESTING ALLOCATION | 1999783.63
104 | 2020/SGP/PAD/461/B/108 | Development of road near Mrs. Deepa's houses at Govijana Mawatha, Udumulla. | Padukka | 461/B | Udumulla | I | m | 140*2.43 | 500000 |  | 499683.66 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 60 |  |  |  | 499759.82
105 | 2020/SGP/PAD/461/B/109 | Development of Udumulla Madagewatta road and by-road from Mr. Vithana's home | Padukka | 461/B | Udumulla | I | m | 85.365* 2.439 | 500000 |  | 499962.68 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 45 |  |  |  | 799999.38
106 | 2020/SGP/PAD/461/C/110 | Development of the "Kreedangana Mavatha" at the 5th lane from Mr.Layan's home to Mr.Udaya's home | Padukka | 461/C | Pahala Padukka | I | m | 93.9* 3.658 | 500000 |  | 499860.23 | D.S Office Padukka |  | 494911.11 | 2474.56 | 497385.67 | [8 empty] | 1 | [6 empty] | 31 |  |  |  | 699894.38
107 | 2020/SGP/PAD/461/C/111 | Concreating & constructing the drain system near mr. Lalith's home at Kumara mawatha | Padukka | 461/C | Pahala Padukka | I | m | 32.926 | 500000 |  | 499655.61 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 114 |  |  |  | 499865.89
108 | 2020/SGP/PAD/461/C/112 | Development of by road at Nimalsirimavatha From Mr. Ajith's home to Mr. Wikkramaraththana's home | Padukka | 461/C | Pahala Padukka | I | m | 73.17* 3.048 | 500000 |  | 498855.89 | D.S Office Padukka |  | 493916.71 | 2469.59 | 496386.3 | [8 empty] | 1 | [6 empty] | 37 |  |  |  | 499995.56
109 | 2020/SGP/PAD/461/C/113 | Development of the Drain System at Kreeda Mavatha from the main gate of Siri Piyarathana vidyalaya and forward | Padukka | 461/C | Pahala Padukka | I | m | 25.91 | 500000 |  | 499779.41 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 436 |  |  | REQUESTING ALLOCATION | 499865.89
110 | 2020/SGP/PAD/461/D/114 | Developing the road near the Chaminda stores at Palpola | Padukka | 461/D | Beliaththavila | I | m | 132*2.74 | 500000 |  | 499995.46 | D.S Office Padukka |  | 495045.02 | 2475.22 | 497520.24 | [7 empty] | 1 | [7 empty] | 40 |  |  |  | 1999591.53
111 | 2020/SGP/PAD/462/115 | Development of Gammana road from biggining | Padukka | 462 | Liyanvala | I | m | 255*3 | 2000000 |  | 1999783.63 | D.S Office Padukka |  | 1979983.79 | 9899.92 | 1989883.71 | [7 empty] | 1 | [7 empty] | 163 |  |  |  | 499981.92
112 | 2020/SGP/PAD/462/A/116 | Development of the Centre which helds maternity Clinic (with chain link fence) | Padukka | 462/A | Poregedara | VI | m | 38.1 | 500000 |  | 499759.82 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 1210
113 | 2020/SGP/PAD/462/A/117 | Development of Amuna road from Edanda road at Poregedara | Padukka | 462/A | Poregedara | I | m | 195*3 | 800000 |  | 799999.38 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 43 |  |  |  | 499981.92
114 | 2020/SGP/PAD/462/A/118 | Development of the by road at Amuna road | Padukka | 462/A | Poregedara | I | m | 190*2.74 | 700000 |  | 699894.38 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 60 |  |  |  | 1999783.63
115 | 2020/SGP/PAD/463/119 | Development of the road at Eastern side of the Jayamuthugama ground which connect 1st and 2nd by roads at Samagipura | Padukka | 463 | Madulava North | I | m | 73.17*3 | 500000 |  | 499865.89 | D.S Office Padukka |  | 494916.73 | 2474.58 | 497391.31 | [7 empty] | 1 | [7 empty] | 1300 |  |  |  | 1999783.63
116 | 2020/SGP/PAD/463/120 | Development of the latter part of Samagi mavatha from Mrs Dayani's home | Padukka | 463 | Madulava North | I | m | 120*3 | 500000 |  | 499995.56 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 420 |  |  | REQUESTING ALLOCATION | 499996.51
117 | 2020/SGP/PAD/463/121 | Development of Pilip road from Mrs Nanadaseeli's home | Padukka | 463 | Madulava North | I | m | 73.17*3 | 500000 |  | 499865.89 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 700 |  |  | REQUESTING ALLOCATION | 499808.95
118 | 2020/SGP/PAD/463/A/122 | Developping the Gammana road from Mrs.Samanthi's home at Madulawa South. | Padukka | 463/A | Madulawa South | I | m | 377*3 | 2000000 |  | 1999591.53 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 305 |  |  | REQUESTING ALLOCATION | 499808.95
119 | 2020/SGP/PAD/464/123 | Rehabilitating the Samanala Mawatha near the Edinbaro Company. | Padukka | 464 | Horagala East | I | m | 121*3 | 500000 |  | 499981.92 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 250 |  |  |  | 499808.95
120 | 2020/SGP/PAD/464/124 | Rehabilitating the Meda cannal across the Duw Millanthotuwa Nugedeniya . | Padukka | 464 | Horagala East | IV |  |  | 500000 |  |  | Provincial Irrigation office | [9 empty] | 1 | [9 empty] | 800 |  |  |  | 499865.89
121 | 2020/SGP/PAD/464 /125 | Developping the cemetry Road and first lane at Horagala east (By Road). | Padukka | 464 | Horagala East | I | m | 121*3 | 500000 |  | 499981.92 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 110 |  |  |  | 499493.29
122 | 2020/SGP/PAD/464/A/126 | Developing the which go to Kongahawila road from Mr. roopasena's home. | Padukka | 464/A | Dhampe | I | m | 255*3.04 | 2000000 |  | 1999783.63 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 248 |  |  | REQUESTING ALLOCATION | 499493.29
123 | 2020/SGP/PAD/464/C/127 | Developping the Dambugollawaththa road from mr. Wijesiri's home to ahead | Padukka | 464/C | Horakandawila | I | m | 210*3.65 | 2000000 |  | 1999783.63 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 291 |  |  |  | 499246.64
124 | 2020/SGP/PAD/464/D/128 | Developing & constructing the retaining wall from Alubogaha paddy at Minuwandeniya paddy field | Padukka | 464/D | Beruketiya | I | m | 17.68 | 500000 |  | 499996.51 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 15 |  |  |  | 499279.63
125 | 2020/SGP/PAD/464/D/129 | Developing Jonna Kanda 280 main road to 2nd lane of Pathum Uyana | Padukka | 464/D | Beruketiya | I | m | 100*3.65 | 500000 |  | 499808.95 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 29 |  |  | REQUESTING ALLOCATION | 499890.89
126 | 2020/SGP/PAD/464/D/130 | Developing Paradise Udyanay aroad near by Mr: Thilina' residence | Padukka | 464/D | Beruketiya | I | m | 100*3.65 | 500000 |  | 499808.95 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 33 |  |  | REQUESTING ALLOCATION | 499890.89
127 | 2020/SGP/PAD/464/D/131 | Developing the byroad from biggining infront of the Mr:Anil Nishantha's residence at gangani udyanaya | Padukka | 464/D | Beruketiya | I | m | 100*3.65 | 500000 |  | 499808.95 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 29 |  |  | REQUESTING ALLOCATION | 499865.89
128 | 2020/SGP/PAD/465/132 | Developing the Road from Mr: Sarath's home at Egodapitiwala | Padukka | 465 | Kurugala | I | m | 73.17* 3.048 | 500000 |  | 499865.89 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 27 |  |  | REQUESTING ALLOCATION | 499890.89
129 | 2020/SGP/PAD/466/133 | Developing the middle part of the Eriyaketiya Colony Road from Mr.Piyadasa's home ,(no. 14) | Padukka | 466 | Meeriyagalla | I | m | 92.073* 2.439 | 500000 |  | 499493.29 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 130 |  |  | REQUESTING ALLOCATION | 499710.79
130 | 2020/SGP/PAD/466/134 | Developing the "Kanda Para" by road from mr. Dharmasena's home at Meeriyagalla(no.143) | Padukka | 466 | Meeriyagalla | I | m | 92.073* 2.439 | 500000 |  | 499493.29 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 85 |  |  | REQUESTING ALLOCATION | 499890.89
131 | 2020/SGP/PAD/466/135 | Developing Polhena second by road from biginning at Meeriyagalla | Padukka | 466 | Meeriyagalla | I | m | 74.085* 3.0487 | 500000 |  | 499246.64 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 33 |  |  | REQUESTING ALLOCATION | 499788.76
132 | 2020/SGP/PAD/466/136 | Developing the two short by roads at Malegedarawaththa from mr. Disanayaka's home ( two joined road) | Padukka | 466 | Meeriyagalla | I | m | 65.548* 2.439 60.06* 3.28 | 500000 |  | 499279.63 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 35 |  |  | REQUESTING ALLOCATION | 999975.65
133 | 2020/SGP/PAD/467/137 | Developing Cemetry road,( Siyabalagaha road) with culvert | Padukka | 467 | Malagala | I | m | 81.097* 2.7439 | 500000 |  | 499890.89 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 120 |  |  | REQUESTING ALLOCATION
134 | 2020/SGP/PAD/467/138 | Developing the first lane of Polkanda road( go to the Wendesi Kella) | Padukka | 467 | Malagala | I | m | 81.097* 2.7439 | 500000 |  | 499890.89 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 120 |  |  | REQUESTING ALLOCATION | 499937.12
135 | 2020/SGP/PAD/467/139 | From Developing Muruthagahahena Road near by P.D Nanda Piyasili' residence | Padukka | 467 | Malagala | I | m | 73.17* 3.048 | 500000 |  | 499865.89 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 60 |  |  | REQUESTING ALLOCATION | 499968.25
136 | 2020/SGP/PAD/467/140 | Concreating & developing the damaged part of the Malagala kanda cross road near mr. Chaminda Senadeera's home. | Padukka | 467 | Malagala | I | m | 81.09* 2.743 | 500000 |  | 499890.89 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 80 |  |  |  | 499968.25
137 | 2020/SGP/PAD/467/A/141 | Developing the road from Malagala kahawala main road near Play ground | Padukka | 467/A | Kahawala | I | m | 30.487* 3.658 | 500000 |  | 499710.79 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 1018 |  |  | REQUESTING ALLOCATION | 499882.86
138 | 2020/SGP/PAD/467/A/142 | Developing the 1st by road from bigining in Piburagala Road | Padukka | 467/A | Kahawala | I | m | 81.097* 2.7439 | 500000 |  | 499890.89 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 116 |  |  | REQUESTING ALLOCATION | 499971.83
139 | 2020/SGP/PAD/467/A/143 | Developing the Kahawala Yatawathura by road from biggining | Padukka | 467/A | Kahawala | I | m | 29.26* 3.048 (with culvert) | 500000 |  | 499788.76 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 43 |  |  | REQUESTING ALLOCATION
140 | 2020/SGP/PAD/467/A/144 | Developing road near the Mr. Buddadasa's residence at Meegahakanda road | Padukka | 468 | Yatawathura | I | m | 242*3 | 1000000 |  | 999975.65 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 100 |  |  | REQUESTING ALLOCATION
141 | 2020/SGP/PAD/467/A/145 | From constructing retaining wall in Yatawathura Rathmalgoda Road(near by Kandagolla Road) | Padukka | 468 | Yatawathura | I |  |  | 1000000 |  |  | Provincial Irrigation office | [9 empty] | 1 | [9 empty] | 200 |  |  |  | 463124.6
142 | 2020/SGP/PAD/453/B/146 | Developing the byroad from mr.Pramuditha's home to ahead at Akkara 8 road | Padukka | 453/B | Pitumpe South | I | m | 74.08* 3.04 | 500000 |  | 499937.12 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 75 |  |  |  | 499966.89
143 | 2020/SGP/PAD/461/D/147 | Developing the road from Mrs. Kalyani's home to ahead at Namal Mawatha. | Padukka | 461/D | Beliaththavila | I | m | 73.17 * 3.048 | 500000 |  | 499968.25 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 202 |  |  |  | 1999954.03
144 | 2020/SGP/PAD/461/D/148 | Developing the road mrs.Ranjani Hemalatha Mapatuna's home to ahead at Namal mawatha. | Padukka | 461/D | Beliaththavila | I | m | 73.17* 3.048 | 500000 |  | 499968.25 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 40 |  |  |  | 499890.89
145 | 2020/SGP/PAD/461/D/149 | Developing the road from bigining near Mr.Wijedasa's home at Araliya mawatha | Padukka | 461/D | Beliaththavila | I | m | 81.097* 2.743 | 500000 |  | 499882.86 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 76 |  |  |  | 1499995.84
146 | 2020/SGP/PAD/463/150 | Developing the road from Mr. Piyadasa's home to ahead (Remaining part of Temple Road) | Padukka | 463 | madulawa North | I | m | 61.28 * 3.658 | 500000 |  | 499971.83 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 700 |  |  |  | 499865.89
147 | 2020/SGP/PAD/464/151 | Constructing the retaining wall at Bomaluwa Korodanda main canal | Padukka | 464 | Horagala East | IV |  |  | 500000 |  |  | Provincial Irrigation office | [9 empty] | 1 | [9 empty] | 30 |  |  |  | 499824.64
148 | 2020/SGP/PAD/465/152 | Constructing the retaining wall at Kolainna canal .(from Pre school to Mr.Padmasiri Hadaragama's Paddy field) | Padukka | 465 | Kurugala | IV |  |  | 1000000 |  |  | Provincial Irrigation office | [9 empty] | 1 | [9 empty] | 55
149 | 2020/SGP/PAD/465/153 | Developing the Arabbada common well road (from No.58,ms.Rosalin Hadaragama's home to ahead) | Padukka | 466 | Kurugala | I | m | 38.1* 2.439 drain 39.63 | 500000 |  | 463124.6 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 95
150 | 2020/SGP/PAD/458/154 | Developing the Udawaththa road from main road to ahead | Padukka | 458 | Udagama | I | m | 73.17* 3.048 | 500000 |  | 499966.89 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 55 |  |  | REQUESTING ALLOCATION
151 | 2020/SGP/PAD/464/B/155 | Constructing the vocational trainning centre at Sri sudharmarama temple , Horagala west | Padukka | 464/B | Horagala West | IX | sqm |  | 2000000 |  | 1999954.03 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 75
152 | 2020/SGP/PAD/467/A/156 | Developing the Samarajeewa mawatha from completed place of right side | Padukka | 467/A | Kahawala | I | m | 81.097* 2.7439 | 500000 |  | 499890.89 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 550 |  |  | REQUESTING ALLOCATION
153 | 2020/SGP/PAD/456/157 | Completing the remaining works of Grama sanwardana building for using as maternity clinic at Pinnawala north. | Padukka | 456 | Pinnawala north | VI | sqm | 61.95 | 1500000 |  | 1499995.84 | D.S Office Padukka | [10 empty] | 1 | [8 empty] | 250
154 | 2020/SGP/PAD/457/B/158 | Developing the Wilauda Kandauda road from Pallewasala new bridge to mr. Wasantha's home | Padukka | 457/B | Waga North | I | m | 73.17* 3.0487 | 500000 |  | 499865.89 | D.S Office Padukka | [10 empty] | 1
155 | 2020/SGP/PAD/457/B/159 | Developing the Horasoda road from bigining to mr.Rukmale 's home | Padukka | 457/B | Waga North | I | m | 81.097* 2.743 | 500000 |  | 499824.64 | D.S Office Padukka | [10 empty] | 1
[9 empty] | 92000000 |  | 84917840.29 |  |  | 17320710.98 | 86603.57 | 17407314.55 | [5 empty] | 9 | 116 | 23 | 7 | [6 empty] | 36281
| *1 | 15+16=17
| *2 | home
| *3 | 21/17*100%
Only One Column should be filled (11 or 12)
* Projects should be categorized for following sectors
| Circular Code | Sector name | [14 empty] | ** Physical progress
| I | Village Roads, Culverts, Bridges, Side Drinage etc. | [14 empty] | A - Estimates are being / to be prepared
| II | Warehouses Facilities for Agricultural Production | [14 empty] | B - For Constructions : B-1= Estimates Approved & Bid Documents Prepared, B-2= Quotation / Bid called, B-3= Quotation / Bid Received, B-4= Contract Awarded Other: Identified Institutions/ CBO's to provide Goods / Instruments, Obtain required list of goods, Estimated prepared
| III | Economic Centers including Weekly Faires , Small Shops
| IV | Construction and renovation of Small Tanks ,Canals, Anicuts,Ponds and Agricultural Wells
| V | Community Drinking Water Supply Projects
| VI | Development/Modernization of Rural Health Centers and Providing Facilities | [14 empty] | C - For Constructions : Start construction work,40% completed, Other : placed order for goods
| VII | Providing and Developing Electricity, Water and Sanitary Facilities for Schools | [14 empty] | D - For Constructions : 60% completed Other : Received goods /instruments as per the order
| VIII | Projects for Prevention of Disasters for Human habitants from wild Animals | [14 empty] | E - For Constructions 80% completed Other : Received goods /instruments as per the order
| IX | Other Physical Infrastructure Improvement Projects Which are Directly Contibuted to Rural Economic Development | [14 empty] | G - For Constructions 100 Completed Other : Issued goods and instruments to identified institutions/CBOs